## Register
Feedback Register
Date | Time | Stakeholder Name | Method of Contact | Subject Area | Site Name | Details | Received By | Status | Resolution | Date Resolved
20/04/2023 | 10:30 | Anonymous | Email | Other | Wellington North | A delivery of tracker material was sighted by a property owner reversing up a street that is outside of the TMP requirements. The property owner approached the driver to pass on directions to WEN. LSbp was contatcted by phone then email. I passed on all relevant information to LSbp EPC for action. Action was completed. | 21/04/2023 | Investigation complete | EPC was informed of the issue
2023-09-25 | 9:48 | Anonymous | Email | Construction | Wellington North | Resident called about construction issues. In particular concerned about the noise level from the post drivers and particularly the excavators with rock hammers is not seriously load but is a constant noise most days. As well as a rock hammer operating on a Sunday. Another concern was the amount of dust from the site. | Lightsource bp | Resolved | EPC was informed of the issue | 2023-10-04
2024-02-14 |  | Anonymous | Phone | Stakeholder Engagement |  | A member of the public raised concern that Oone of the workers ute has pulled out in front of another car, nearly causing an accident. | Lightsourcebp | Resolved | Past onto EPC
2024-02-19 |  | Anonymous | Phone | Operation |  | Recieved a call from the neighbour directly south of Wellington South stating that there is a breach in the chainmesh fence created by Roo's allowing them in & out of each property. This neighbour has bought lambs and intends to use the padddock in question. I spoke to O&M He said he will investigate and repair the damage. | Lightsourcebp | Resolved
8686:112

## Data validation
Phone | Construction | Wellington | Very satisfied | Investigating
Letter | Operation | Mid-Murray | Satisfied | Investigation complete
Email | Environmental Matters | Mokoan & Mokoan Extension | Neither | Action proposed
| Stakeholder Engagement | Naring | Not satisfied | Action complete
| Other | West Wyalong | Escalating | Resolved
|  | Woolooga |  | Unresolved